## Sheet1
Phase | Task | Hours | Hourly Rate ($) | Cost ($)
Planing |  | 115 |  | 1528
| Identify Project Req.s | 3 | 5 | 15
| Identify Stakeholders | 5 | 5 | 25
| Create Stakeholders engagement Plan | 4 | 7 | 28
| Create Project Charter | 16 | 10 | 160
| Create Team Charter. | 8 | 15 | 120
| Create risk management plan. | 24 | 20 | 480
| Create time estimation for project. | 30 | 15 | 450
| Create schedule for project. | 25 | 10 | 250
Designing |  | 130 |  | 3250
| Create Software Architechare | 72 | 25 | 1800
| prototype Design | 10 | 25 | 250
| Improving Site Performance | 48 | 25 | 1200
Implementation |  | 630 |  | 18900
| Create Ui/UX | 150 | 30 | 4500
| Create Frontend | 240 | 30 | 7200
| Create Backend | 240 | 30 | 7200
Monitoring & Testing |  | 102 |  | 1530
| Test Configuration | 30 | 15 | 450
| Reviewing Design | 42 | 15 | 630
| Releasing The Site | 30 | 15 | 450
|  |  | Tools Tools Cost | 25208
Tools |  | Description | Cost ($)/Month | Note
| Dedicated Server (Hosting) | Processors:1 CPU Cores:16 CPU Threads:16 Base Freq:2.1 1TB HDD & 32GB RAM | 120
| SSL Certification | Free SSL | 0
| Domain name | .com domain | 1
| App store license | App Store | 12
| Google play License | Google Play | 42 | One time payment
| Microsoft store License | Microsoft Store | 110 | One time payment
| Cloudflare License | Pro Plan | 30
| Video Streaming | Video | $0.01/GB (min 9 $/m) | Based on using
| Tickiting System | Tickiting | 80
| Chat Plugin | Chat | 35
| Marketing analysis Plugin | Marketing Analysis | 20
| Payment Gateway Fees | Payment Gateway | 75
|  |  | Tools Tools Cost | 382
|  |  | One time Costs | 140
|  |  | Total Project Costs ($) | 25730
|  |  | Total Monthly Costs ($) | 382